## Slide 1: PathaSathi 6-month launch plan
A 5-person tech team in Dhaka, a staged business and operations team in New York, and the monthly cost of each
Team size by month: 5 people at kickoff, 15 by Month 6
Chart: 
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Dhaka tech team | 5 | 5 | 5 | 5 | 5 | 5
New York team | 0 | 0 | 2 | 3 | 6 | 10

## Slide 2: Summary
SIX-MONTH BUDGET
$213.4K
All-in, including 10% contingency. Average $35.6K per month, peaking at $77.7K in Month 6.
5
people in the Dhaka tech team, Project Manager included, fixed for all six months
10
New York hires by Month 6: operations, finance, sales, support and field staff
$80K
monthly run-rate from Month 7 with a team of 15
Pilot target 150–200 merchants serving 1,500–2,000 customers

## Slide 3: Operating model
Dhaka: tech team
Project management : 1
Backend development : 2
Frontend and mobile app : 1
QA, DevOps and cloud : 1
Total salaries, 5 people : $26,400
New York: business and ops
Operations : Operations Manager (leads New York)
Finance : Finance and Compliance (part-time)
Growth : 3 Sales Executives
Merchant success : support agents, field officers
Service data : Sales Executives, on contract
Advisory : US legal and fintech retainer
Total salaries, 10 people : $81,700

## Slide 4: Build roadmap
Month 1
Month 2
Month 3
Month 4
Month 5
Month 6
1 Discovery, DB schema and UX spec
2 Multi-tenant backend and auth
3 Core engine: directory, map, feed
4 Marketplace: catalogue, cart, checkout
5 Stripe payments, maps and courier APIs
6 AI assistant, notifications, marketing hub
7 QA and beta: 150–200 merchants
8 Launch: onboard 1,500–2,000 customers
3 wks
3 wks
4 wks
3 wks
3 wks
3 wks
3 wks
2 wks

## Slide 5: Staged hiring gates
Kickoff · Day 1
Funding in place and US company (Delaware C-corp, NY registration) set up
Releases Month 1 hires. Dhaka: the full team of 5. No New York hires yet.
G1 · end of M1
Discovery done: database schema and UX spec signed off
No new hires. Founders build the merchant, partner and community pipeline.
G2 · end of M2
Multi-tenant backend and auth demoed end to end
Releases Month 3 hires. Operations Manager, Finance (part-time).
G3 · end of M3
Directory, map and marketplace working in staging
Releases Month 4 hires. First Sales Executive; service data contract starts.
G4 · end of M4
Stripe, maps and courier sandboxes passing
Releases Month 5 hires. 2 support agents, 2nd Sales Executive.
G5 · end of M5
Beta live: 150–200 merchants, 1,500–2,000 customers, 5 service directories filled
Releases Month 6 hires. 3rd Sales Executive, 3rd support agent, 2 field officers.

## Slide 6: Headcount by month
Dhaka tech team
New York team
Total people at the end of each bar · who joins, at far right
Chart: 
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Dhaka tech team | 5 | 5 | 5 | 5 | 5 | 5
New York team | 0 | 0 | 2 | 3 | 6 | 10
Month 1
5
Dhaka Full team of 5. No New York hires yet.
Month 2
5
No new hires. Dhaka stays at 5.
Month 3
7
New York Operations Manager, Finance (part-time).
Month 4
8
New York First Sales Executive; service data contract starts.
Month 5
11
New York 2 support agents, 2nd Sales Executive.
Month 6
15
New York 3rd Sales Executive, 3rd support agent, 2 field officers.

## Slide 7: Dhaka tech team: 5 people by function
Function | Salary BDT/m | Salary USD/m | M1 | M2 | M3 | M4 | M5 | M6 | Person-months
Project Manager | 130,000 | 1,050 | 1 | 1 | 1 | 1 | 1 | 1 | 6
Backend Developer (×2) | 117,000 | 950 | 2 | 2 | 2 | 2 | 2 | 2 | 12
Frontend and mobile app Developer | 89,000 | 700 | 1 | 1 | 1 | 1 | 1 | 1 | 6
QA, DevOps and Cloud | 93,000 | 750 | 1 | 1 | 1 | 1 | 1 | 1 | 6
Total people |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 30

## Slide 8: Dhaka tech team: salary cost by function
Function | M1 | M2 | M3 | M4 | M5 | M6 | 6-month total
Project Manager | 1,050 | 1,050 | 1,050 | 1,050 | 1,050 | 1,050 | 6,300
Backend Developer (×2) | 1,900 | 1,900 | 1,900 | 1,900 | 1,900 | 1,900 | 11,400
Frontend and mobile app Developer | 700 | 700 | 700 | 700 | 700 | 700 | 4,200
QA, DevOps and Cloud | 750 | 750 | 750 | 750 | 750 | 750 | 4,500
Total tech salaries (US$) | 4,400 | 4,400 | 4,400 | 4,400 | 4,400 | 4,400 | 26,400

## Slide 9: New York team
Role | Pay basis | Salary USD/m | M1 | M2 | M3 | M4 | M5 | M6
Operations Manager | $66K / year | 5,500 | – | – | 1 | 1 | 1 | 1
Finance and Compliance (part-time) | $30K / year | 2,500 | – | – | 1 | 1 | 1 | 1
Sales Executive (merchant acquisition) | $50K / year | 4,200 | – | – | – | 1 | 2 | 3
Support Agent (Bangla + English) | $42K / year | 3,500 | – | – | – | – | 2 | 3
Field Support Officer | $42K / year | 3,500 | – | – | – | – | – | 2
Total headcount |  |  | – | – | 2 | 3 | 6 | 10

## Slide 10: New York team: monthly cost by role
Role | M1 | M2 | M3 | M4 | M5 | M6 | 6-month total
Operations Manager | – | – | 5,500 | 5,500 | 5,500 | 5,500 | 22,000
Finance and Compliance (part-time) | – | – | 2,500 | 2,500 | 2,500 | 2,500 | 10,000
Sales Executive (merchant acquisition) | – | – | – | 4,200 | 8,400 | 12,600 | 25,200
Support Agent (Bangla + English) | – | – | – | – | 7,000 | 10,500 | 17,500
Field Support Officer | – | – | – | – | – | 7,000 | 7,000
Total New York team (US$) | – | – | 8,000 | 12,200 | 23,400 | 38,100 | 81,700

## Slide 11: Service data collection
5
services at launch, collected by Sales Executives on contract
$1,000 per service
one-time contract fee, about 150 verified listings
$5,000 before beta
then $500–$1,500 a month, only when needed
Months 4–5
At launch
Jobs
Housing
Free food
Legal aid
Hospitals and clinics
When needed
Next
Pharmacy
Embassy and consulate
Halal food
Grocery
Education and ESL
Transit
Religion
Social aid
When needed
Later
Free medicine
Money exchange
Travel and flights
Cars and auto
Electronics
Furniture
Gas and EV
Sports

## Slide 12: Other operating costs
Item | Basis | 6-month total
Cloud hosting and APIs | Scales with merchants: $300 in M1 to $2,500 in M6 (hosting, maps, AI) | 7,100
Tech tools: AI, design, testing | $300/mo: AI tools $120, Figma $45, BrowserStack $50, GitHub/Jira/Slack $85 | 1,800
Service data collection (contract) | $1,000 per service paid to Sales Executives: 2 services in M4, 3 in M5 | 5,000
Dhaka workspace | $30 per person per month: desk and internet | 900
New York co-working (Queens) | $350 per desk per month for full- and part-time office staff | 7,350
Go-to-market | Ads, SMS, merchant demos and community events from M4: $1,500 to $6,500 | 12,000
Legal and fintech advisory | $2,000/mo US counsel retainer plus $5,000 company set-up in M1 | 17,000
Business insurance | General liability and cyber cover, $400 per month | 2,400
Field transit (OMNY) | $135 per month for sales and field staff | 1,080
Computers and devices | 3 MacBooks, 5 laptops, 5 tablets, 5 printers, 2 phones, 3 headsets | 10,299
Dhaka–New York travel | Two trips at $3,000: discovery in M1 and launch in M6 | 6,000
US payroll taxes (10%) | Employer FICA, unemployment insurance and workers' comp on US wages | 8,170
Health stipend | $400 per month for each full-time US employee | 6,800
Total operating costs |  | 85,899

## Slide 13: Computers and devices
8
computers: 3 MacBook Air in Dhaka, 5 office laptops in New York
US$1,065
average per computer: MacBook Air US$1,341, New York laptop US$899
US$10,299
all devices, one-time, bought only when each person joins
Item | For | Bought | Qty | Unit US$ | Total US$
MacBook Air M3 (16GB, 1TB) | Dhaka developers | M1 | 3 | 1,341 | 4,023
Android test phone (Galaxy A06) | Dhaka QA testing | M1 | 2 | 114 | 228
Office laptop (i5, 16GB, 512GB) | US operations, finance, support | M3, M5–M6 | 5 | 899 | 4,495
Android tablet (Galaxy Tab A9+) | Sales, field | M4–M6 | 5 | 220 | 1,100
Bluetooth receipt printer (58mm) | Merchant demo kits | M4–M6 | 5 | 69 | 345
USB headset | Support agents | M5–M6 | 3 | 36 | 108
Total |  |  | 23 |  | 10,299

## Slide 14: Monthly spend and cumulative budget
Dhaka tech team
New York team
Other operating
Contingency
Chart: 
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Dhaka tech team | 4400 | 4400 | 4400 | 4400 | 4400 | 4400
New York team | 0 | 0 | 8000 | 12200 | 23400 | 38100
Other operating | 15401 | 3350 | 7348 | 11113 | 20588 | 28099
Contingency | 1980 | 775 | 1975 | 2771 | 4839 | 7060
Month 1
$21.8K
Cumulative $21.8K
Month 2
$8.5K
Cumulative $30.3K
Month 3
$21.7K
Cumulative $52.0K
Month 4
$30.5K
Cumulative $82.5K
Month 5
$53.2K
Cumulative $135.7K
Month 6
$77.7K
Cumulative $213.4K

## Slide 15: Where the money goes
12.4%
38.3%
40.3%
9.1%
Dhaka tech salaries
$26,400
5 people × 6 months
New York team
$81,700
21 person-months; service data on contract
Other operating
$85,899
Payroll taxes, devices, legal, office, transit, cloud, marketing
Contingency
$19,400
10% of all costs

## Slide 16: Scenarios and sensitivity
Hybrid lean base: this plan
Dhaka tech + New York business and ops team
$213K
Premium talent
+40% Dhaka salaries and +25% New York pay
$250K
Dedicated data team
21 part-time associates, one per service
$356K
All-US engineering
5 New York engineers at about $150K a year each
$651K

## Slide 17
FUNDING REQUIREMENT
$454K
completes the six-month build and funds Months 7–9 at the launch run-rate, with no revenue assumed.
Month 6
$213.4K
Build complete, 15 people, beta live
Month 9
$454K
Three months of runway
Month 12
$695K
Six months of runway

## Slide 18: PathaSathi business model
Plan | Price per month | What the merchant gets
Free | $0 | Map listing, basic catalogue, 1 user, with ads
Basic | $19 | Full catalogue and orders, verified badge, customer SMS reminders, reports, no ads
Pro | $49 | Multi-staff, online storefront and delivery, marketing hub, AI advice, priority listing, no ads
Payment commission
0.5% on online payments via Stripe Connect split payments, on top of Stripe's own fee
SMS credits
Bulk SMS resold with a small margin, about US$1.50 per paid merchant per month
Ads
Banner ads for customers and free-plan merchants only, never at checkout: about US$0.08 per active customer a month

## Slide 19: How merchants get onboarded
1
Day 0
Visit and demo
A 10-minute demo on the merchant's phone, in the shop
Sales Executive
2
Same day
Free sign-up
Merchant signs up with a phone number and a map pin on the Free plan
Sales Executive
3
Days 1–3
Shop set-up
Products added by barcode or AI photo scan, plus prices, delivery zones and Stripe payouts
Sales Executive
4
First 30 days
Training and check-ins
Training in Bangla or English, check-ins in weeks 1 and 3; each merchant invites first 10 customers
Support Agent
5
Month 1–2
Upgrade to paid
When the merchant needs a verified badge, SMS reminders or an online store
$19 or $49
Year 1 funnel
3,795
merchants join and upgrade to paid
2,799
merchants still paying at year end
27,990
active customers (10 per merchant)

## Slide 20: After launch
Months 5–6
Beta
150–200 beta merchants in Queens
1,500–2,000 customers, 10 per merchant
Jackson Heights, Jamaica, Ozone Park
Fix bugs from feedback
200 ready to pay
2,000 customers
Year 1
New York City
Door-to-door merchant sales
Brooklyn and Bronx (Parkchester)
Bangla media, Facebook, TikTok
Referral: 1 free month
2,799 paid merchants
27,990 customers
Year 2
NJ and Michigan
Paterson, New Jersey
Detroit and Hamtramck
Mosque and community partners
WhatsApp broadcasts
6,789 paid merchants
67,890 customers
Years 3–5
Nationwide
Atlanta, Texas, California
Other South Asian communities
Brand-sponsored ads
Annual plans
20,290 paid merchants
202,900 customers

## Slide 21: Merchant and customer growth
1 : 10
every active merchant serves about ten active customers
Beta 150–200 merchants →
1,500–2,000 customers
Year 5 20,290 merchants →
202,900 customers
Chart: Active customers
| Beta | Month 12 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Active customers | 2000 | 12530 | 27990 | 67890 | 115870 | 162550 | 202900
 | Beta | Month 12 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Merchants | 150–200 | 1,253 | 2,799 | 6,789 | 11,587 | 16,255 | 20,290
Customers | 1,500–2,000 | 12,530 | 27,990 | 67,890 | 115,870 | 162,550 | 202,900

## Slide 22: First 6 months of revenue
Month | New merchants | Paid merchants | Customers | Subscriptions | Pay + SMS | Ads | Revenue | Cost | Net (US$)
Month 7 | 200 | 200 | 2,000 | 5,900 | 1,500 | 160 | 7,560 | 80,338 | −72,778
Month 8 | 216 | 402 | 4,020 | 11,859 | 3,015 | 322 | 15,195 | 80,978 | −65,783
Month 9 | 233 | 607 | 6,070 | 17,910 | 4,553 | 486 | 22,949 | 81,661 | −58,712
Month 10 | 252 | 817 | 8,170 | 24,088 | 6,124 | 653 | 30,865 | 82,392 | −51,527
Month 11 | 272 | 1,031 | 10,310 | 30,428 | 7,736 | 825 | 38,989 | 83,175 | −44,186
Month 12 | 294 | 1,253 | 12,530 | 36,966 | 9,398 | 1,002 | 47,366 | 84,015 | −36,649
Total | 1,467 |  |  | 127,151 | 32,326 | 3,448 | 162,924 | 492,559 | −329,635

## Slide 23: Five years revenue
Year | New paid merchants | Paid merchants at year end | Customers at year end | Ads (US$) | Revenue (US$) | Avg/month (US$)
Year 1 | 3,795 | 2,799 | 27,990 | 13,621 | 643,582 | 53,632
Year 2 | 7,287 | 6,789 | 67,890 | 49,816 | 2,353,788 | 196,149
Year 3 | 10,214 | 11,587 | 115,870 | 92,404 | 4,366,112 | 363,843
Year 4 | 12,129 | 16,255 | 162,550 | 137,530 | 6,498,273 | 541,523
Year 5 | 12,804 | 20,290 | 202,900 | 178,594 | 8,438,573 | 703,214
Total | 46,229 |  |  | 471,965 | 22,300,328 | 

## Slide 24: Break-even point
US$80,338
cost in launch month: team of 15 plus operating costs, rising as merchants grow
US$37.80
average monthly revenue per paid merchant, incl. US$0.80 from ads
~2,799
paid merchants (~27,990 customers) when revenue first covers costs, Month 12 after launch
Case | Monthly break-even | 5-year revenue
Growth case (this forecast) | Month 12 | US$22.3M
Conservative (half the merchant growth) | Month 19 | US$11.2M

## Slide 25: Profit or loss
+US$9.38M
cumulative profit after 5½ years, growth case
Month 12
after launch: first month revenue covers costs
−US$0.66M
lowest cumulative point, Month 13 after launch: the funding needed
Period | Revenue | Costs | Profit / loss | Cumulative | If growth is half
Build | 0 | 213,399 | −213,399 | −213,399 | −213,399
Year 1 | 643,582 | 1,068,029 | −424,447 | −637,846 | −842,457
Year 2 | 2,353,788 | 1,792,174 | 561,614 | −76,232 | −905,543
Year 3 | 4,366,112 | 2,565,073 | 1,801,039 | 1,724,807 | −344,004
Year 4 | 6,498,273 | 3,360,546 | 3,137,727 | 4,862,534 | 851,428
Year 5 | 8,438,573 | 3,925,644 | 4,512,929 | 9,375,463 | 2,706,026
Total | 22,300,328 | 12,924,865 | 9,375,463 |  | 2,706,026

## Slide 26: Thank you

## Slide 27: Month 1 plan: at a glance
Month 1 goal Gate G1: database schema and UX spec signed off, company set up, login build started
Week 1
Kickoff and audit
Founder in Dhaka for kickoff
Tools and access set up
Audit of the React prototype
Delaware C-corp filed
Outcome: Audit report and risk list
Week 2
Requirements
PRD v1 and user journeys
Database model (ERD) v1
UX designer starts
First 15 merchant interviews
Outcome: PRD and ERD v1 reviewed
Week 3
Design and set-up
API contract (OpenAPI) final
CI/CD, dev and staging live
Exposed API keys rotated
30 interviews, 5 services chosen
Outcome: Schema and API signed off
Week 4
Build starts
Backend skeleton and migrations
Phone OTP login and roles
App shell wired to the API
25 UX screens signed off
Outcome: Gate G1 passed

## Slide 28: Month 1 plan: daily and weekly rhythm
Every day (Dhaka, Sunday–Thursday)
10:00
15-minute stand-up: yesterday, today, blockers
10:15–13:00
Focus block 1, no meetings
14:00–17:00
Focus block 2; code reviews done by 17:00
17:30
Code pushed; staging deploys automatically
19:30
30-minute sync with founders (9:30 am New York, Mon–Thu)
End of day
Jira updated; blockers posted in Slack
Every week
Sunday
Sprint planning (1 hour): pick the week's tickets
Monday
Founders share merchant interview insights
Wednesday
Design review with the UX designer; architecture review
Thursday
Demo on staging, retro, weekly report to founders
Friday
Dhaka weekend; New York merchant interviews
Saturday
Dhaka weekend; founders set next week's priorities
Time zones Dhaka is 10 hours ahead of New York (11 in winter). The daily sync uses the overlap: 7:30 pm Dhaka, 9:30 am New York.

## Slide 29: Month 1 plan: day by day, weeks 1 and 2
Day | Dhaka tech team | Founders and New York
Day 1 · Sun | Kickoff with founder: goals, roles, Gate G1 checklist | Founder in Dhaka; file Delaware C-corp
Day 2 · Mon | Tools set up: Jira, GitHub, Slack, Figma, cloud access | Brief US lawyer; registered agent set up
Day 3 · Tue | Audit the React prototype: what to keep, what to rebuild | Write merchant interview script (15 questions)
Day 4 · Wed | Security plan: rotate BariKoi key, AI key to server | Pick UX designer; sign contract
Day 5 · Thu | Demo: audit report, tech stack, risk list; retro | Founder flies back; hire 2 interview students
Day 6 · Sun | Sprint planning; PRD outline, user roles and journeys | Interviews start: 5 shops in Jackson Heights
Day 7 · Mon | Data model workshop: merchants, stores, products, orders | Apply for EIN; open US bank account
Day 8 · Tue | Database model (ERD) v1 in PostgreSQL + PostGIS | 5 more interviews in Jamaica
Day 9 · Wed | UX kickoff with designer; brand design tokens | Design call: share merchant pain points
Day 10 · Thu | Demo: PRD v1, ERD v1, design brief; retro | Interview summary: top 10 merchant needs
Dhaka works Sunday–Thursday; New York works Monday–Friday.

## Slide 30: Month 1 plan: day by day, weeks 3 and 4
Day | Dhaka tech team | Founders and New York
Day 11 · Sun | PRD v2 with merchant feedback; MVP scope frozen | Choose first 5 services for data collection
Day 12 · Mon | API contract (OpenAPI) v1; multi-tenant design | File NY registration; apply for Stripe account
Day 13 · Tue | CI/CD, Docker and dev environment live | 10 more interviews in Ozone Park
Day 14 · Wed | Staging live; secrets manager; keys rotated | Design review: first 15 screens
Day 15 · Thu | Demo: ERD and API final sign-off; retro | 30 interviews done; insight report
Day 16 · Sun | Sprint 1 planning: backend skeleton and login | Start search for Operations Manager (joins M3)
Day 17 · Mon | Backend skeleton: structure, migrations, seed data | Outreach: 3 mosques, 2 community groups
Day 18 · Tue | Login service: phone OTP (Twilio Verify), JWT | Bookkeeping and payroll set up
Day 19 · Wed | Roles (merchant, customer, admin); app shell on API | All 25 UX screens delivered and signed off
Day 20 · Thu | Gate G1 review: sign-off, Month 2 sprint plan | Founders sign Gate G1; Month 2 released
Dhaka works Sunday–Thursday; New York works Monday–Friday.

## Slide 31: Month 1 plan: who builds what
Role | Modules in Month 1 | Delivered by Day 20
Project Manager | PRD, user journeys, Jira backlog, sprint plans, Gate G1 checklist; runs designer and founder syncs | Signed-off PRD; Month 2 sprint plan
Backend Developer 1 (lead) | Architecture, PostgreSQL + PostGIS schema, multi-tenant model, OpenAPI contract; Week 4: login service | Signed-off ERD and API; OTP login on staging
Backend Developer 2 | Seed data from the prototype, geo search for the directory, Stripe, Mapbox, Twilio and AI spikes; Week 4: merchant APIs | Spike reports; merchant and store APIs started
Frontend and mobile Developer | Prototype audit, split oversized pages, brand design tokens, component library, API client; Week 4: login screens | App shell with login on staging
QA, DevOps and Cloud | GitHub, CI/CD, Docker, dev and staging, secrets manager, rotate exposed keys; MVP test plan | Staging live; test plan v1
UX/UI designer (outsourced) | Design system and 25 key screens from the Figma prototype, in brand colours | 25 screens signed off

## Slide 32: Month 1 plan: outsourcing and cost
$3,420
new outsourcing in Month 1, paid from the 10% contingency
$7,000
legal set-up, already in the Month 1 budget
$25.2K
total Month 1 spend: $21.8K plan + $3.4K new
Work | Who and how | Cost (US$) | In budget?
UX/UI design: design system and 25 key screens | Dhaka freelance designer, 80 hours × $25 | 2,000 | New
US company set-up: Delaware C-corp, NY registration, ToS, privacy | US startup law firm: $5,000 set-up + $2,000 retainer | 7,000 | Yes
Tech team contracts in Bangladesh | Dhaka law firm, one time | 400 | New
Bookkeeping and payroll set-up | US bookkeeping service until Finance joins in Month 3 | 300 | New
Merchant interviews in Queens (30 shops) | 2 students × 20 hours × $18 | 720 | New
Total outsourcing in Month 1 |  | 10,420 | 3,420 new
Not outsourced: all development, QA and DevOps stay with the Dhaka team.

## Slide 33: Month 1 plan: Gate G1 checklist
# | Must be done by the end of Month 1 | Owner | Day
1 | PRD and MVP scope signed off | PM and founders | Day 11
2 | Delaware C-corp, EIN, bank account and Stripe application done | Founders | Day 12
3 | CI/CD, dev and staging environments live | QA, DevOps | Day 14
4 | Exposed API keys rotated; AI key moved to the server | QA, DevOps | Day 14
5 | Database schema (ERD) signed off | Backend lead | Day 15
6 | API contract (OpenAPI) signed off | Backend lead | Day 15
7 | 30 merchant interviews done; first 5 services confirmed | Founders | Day 15
8 | 25 UX screens in brand colours signed off | UX designer and PM | Day 19
9 | Phone OTP login working on staging | Backend and frontend | Day 19
Rule Month 2 work starts only when all nine items are done; a late item moves the plan, not just one task.