## Slide 1: PathaSathi 6-month launch plan
A 5-person tech team in Dhaka, a staged business and operations team in New York, and the monthly cost of each
Team size by month: 5 people at kickoff, 36 by Month 6
Chart: 
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Dhaka tech team | 5 | 5 | 5 | 5 | 5 | 5
New York team | 0 | 0 | 9 | 17 | 27 | 31

## Slide 2: Summary
SIX-MONTH BUDGET
$356.2K
All-in, including 10% contingency. Average $59.4K per month, peaking at $125.4K in Month 6.
5
people in the Dhaka tech team, Project Manager included, fixed for all six months
31
New York hires by Month 6: 10 business and ops staff, 21 part-time service data associates
$128K
monthly run-rate from Month 7 with a team of 36
Pilot target 150–200 merchants serving 1,500–2,000 customers

## Slide 3: Operating model
Dhaka: tech team
Project management : 1
Backend development : 2
Frontend and mobile app : 1
QA, DevOps and cloud : 1
Total salaries, 5 people : $26,400
New York: business and ops
Operations : Operations Manager (leads New York)
Finance : Finance and Compliance (part-time)
Growth : 3 Sales Executives
Merchant success : support agents, field officers
Service data : 21 associates, one per service
Advisory : US legal and fintech retainer
Total salaries, 31 people : $190,879

## Slide 4: Build roadmap
Month 1
Month 2
Month 3
Month 4
Month 5
Month 6
1 Discovery, DB schema and UX spec
2 Multi-tenant backend and auth
3 Core engine: directory, map, feed
4 Marketplace: catalogue, cart, checkout
5 Stripe payments, maps and courier APIs
6 AI assistant, notifications, marketing hub
7 QA and beta: 150–200 merchants
8 Launch: onboard 1,500–2,000 customers
3 wks
3 wks
4 wks
3 wks
3 wks
3 wks
3 wks
2 wks

## Slide 5: Staged hiring gates
Kickoff · Day 1
Funding in place and US company (Delaware C-corp, NY registration) set up
Releases Month 1 hires. Dhaka: the full team of 5. No New York hires yet.
G1 · end of M1
Discovery done: database schema and UX spec signed off
No new hires. Founders build the merchant, partner and community pipeline.
G2 · end of M2
Multi-tenant backend and auth demoed end to end
Releases Month 3 hires. Operations Manager, Finance (part-time), 7 data associates.
G3 · end of M3
Directory, map and marketplace working in staging
Releases Month 4 hires. First Sales Executive, 7 data associates.
G4 · end of M4
Stripe, maps and courier sandboxes passing
Releases Month 5 hires. 2 support agents, 2nd Sales Executive, 7 data associates.
G5 · end of M5
Beta live: 150–200 merchants, 1,500–2,000 customers, 21 directories filled
Releases Month 6 hires. 3rd Sales Executive, 3rd support agent, 2 field officers.

## Slide 6: Headcount by month
Dhaka tech team
New York team
Total people at the end of each bar · who joins, at far right
Chart: 
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Dhaka tech team | 5 | 5 | 5 | 5 | 5 | 5
New York team | 0 | 0 | 9 | 17 | 27 | 31
Month 1
5
Dhaka Full team of 5. No New York hires yet.
Month 2
5
No new hires. Dhaka stays at 5.
Month 3
14
New York Operations Manager, Finance (part-time), 7 data associates.
Month 4
22
New York First Sales Executive, 7 data associates.
Month 5
32
New York 2 support agents, 2nd Sales Executive, 7 data associates.
Month 6
36
New York 3rd Sales Executive, 3rd support agent, 2 field officers.

## Slide 7: Dhaka tech team: 5 people by function
Function | Salary BDT/m | Salary USD/m | M1 | M2 | M3 | M4 | M5 | M6 | Person-months
Project Manager | 130,000 | 1,050 | 1 | 1 | 1 | 1 | 1 | 1 | 6
Backend Developer (×2) | 117,000 | 950 | 2 | 2 | 2 | 2 | 2 | 2 | 12
Frontend and mobile app Developer | 89,000 | 700 | 1 | 1 | 1 | 1 | 1 | 1 | 6
QA, DevOps and Cloud | 93,000 | 750 | 1 | 1 | 1 | 1 | 1 | 1 | 6
Total people |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 30

## Slide 8: Dhaka tech team: salary cost by function
Function | M1 | M2 | M3 | M4 | M5 | M6 | 6-month total
Project Manager | 1,050 | 1,050 | 1,050 | 1,050 | 1,050 | 1,050 | 6,300
Backend Developer (×2) | 1,900 | 1,900 | 1,900 | 1,900 | 1,900 | 1,900 | 11,400
Frontend and mobile app Developer | 700 | 700 | 700 | 700 | 700 | 700 | 4,200
QA, DevOps and Cloud | 750 | 750 | 750 | 750 | 750 | 750 | 4,500
Total tech salaries (US$) | 4,400 | 4,400 | 4,400 | 4,400 | 4,400 | 4,400 | 26,400

## Slide 9: New York team
Role | Pay basis | Salary USD/m | M1 | M2 | M3 | M4 | M5 | M6
Operations Manager | $66K / year | 5,500 | – | – | 1 | 1 | 1 | 1
Finance and Compliance (part-time) | $30K / year | 2,500 | – | – | 1 | 1 | 1 | 1
Sales Executive (merchant acquisition) | $50K / year | 4,200 | – | – | – | 1 | 2 | 3
Support Agent (Bangla + English) | $42K / year | 3,500 | – | – | – | – | 2 | 3
Field Support Officer | $42K / year | 3,500 | – | – | – | – | – | 2
Service Data Associate (part-time) | $20/hr × 20 hrs/wk | 1,733 | – | – | 7 | 14 | 21 | 21
Total headcount |  |  | – | – | 9 | 17 | 27 | 31

## Slide 10: New York team: monthly cost by role
Role | M1 | M2 | M3 | M4 | M5 | M6 | 6-month total
Operations Manager | – | – | 5,500 | 5,500 | 5,500 | 5,500 | 22,000
Finance and Compliance (part-time) | – | – | 2,500 | 2,500 | 2,500 | 2,500 | 10,000
Sales Executive (merchant acquisition) | – | – | – | 4,200 | 8,400 | 12,600 | 25,200
Support Agent (Bangla + English) | – | – | – | – | 7,000 | 10,500 | 17,500
Field Support Officer | – | – | – | – | – | 7,000 | 7,000
Service Data Associate (part-time) | – | – | 12,131 | 24,262 | 36,393 | 36,393 | 109,179
Total New York team (US$) | – | – | 20,131 | 36,462 | 59,793 | 74,493 | 190,879

## Slide 11: Service data team
21
services in the app, one Service Data Associate each
$1,733 per month
part-time: $20/hour × 20 hours a week
$109,179 in six months
63 person-months, full-time from Year 2
Joins Month 3
Essentials
Jobs
Housing
Free food
Legal aid
Hospitals and clinics
Pharmacy
Embassy and consulate
Joins Month 4
Daily life
Halal food and restaurants
Grocery
Education and ESL
Transit
Religion
Social aid
Free medicine
Joins Month 5
Marketplace
Money exchange
Travel and flights
Cars and auto
Electronics
Furniture
Gas and EV
Sports

## Slide 12: Other operating costs
Item | Basis | 6-month total
Cloud hosting and APIs | Scales with merchants: $300 in M1 to $2,500 in M6 (hosting, maps, AI) | 7,100
Tech tools: AI, design, testing | $300/mo: AI tools $120, Figma $45, BrowserStack $50, GitHub/Jira/Slack $85 | 1,800
Data collection tools | $25 per data associate per month: Airtable, forms, VoIP calling | 1,575
Dhaka workspace | $30 per person per month: desk and internet | 900
New York co-working (Queens) | $350 per desk per month for full- and part-time office staff | 7,350
Go-to-market | Ads, SMS, merchant demos and community events from M4: $1,500 to $6,500 | 12,000
Legal and fintech advisory | $2,000/mo US counsel retainer plus $5,000 company set-up in M1 | 17,000
Business insurance | General liability and cyber cover, $400 per month | 2,400
Field transit (OMNY) | $135 per month for data associates, sales and field staff | 9,585
Computers and devices | 3 MacBooks, 5 laptops, 26 tablets, 5 printers, 2 phones, 3 headsets | 14,919
Dhaka–New York travel | Two trips at $3,000: discovery in M1 and launch in M6 | 6,000
US payroll taxes (10%) | Employer FICA, unemployment insurance and workers' comp on US wages | 19,087
Health stipend | $400 per month for each full-time US employee | 6,800
Total operating costs |  | 106,516

## Slide 13: Computers and devices
8
computers: 3 MacBook Air in Dhaka, 5 office laptops in New York
US$1,065
average per computer: MacBook Air US$1,341, New York laptop US$899
US$14,919
all devices, one-time, bought only when each person joins
Item | For | Bought | Qty | Unit US$ | Total US$
MacBook Air M3 (16GB, 1TB) | Dhaka developers | M1 | 3 | 1,341 | 4,023
Android test phone (Galaxy A06) | Dhaka QA testing | M1 | 2 | 114 | 228
Office laptop (i5, 16GB, 512GB) | US operations, finance, support | M3, M5–M6 | 5 | 899 | 4,495
Android tablet (Galaxy Tab A9+) | Data associates, sales, field | M3–M6 | 26 | 220 | 5,720
Bluetooth receipt printer (58mm) | Merchant demo kits | M4–M6 | 5 | 69 | 345
USB headset | Support agents | M5–M6 | 3 | 36 | 108
Total |  |  | 44 |  | 14,919

## Slide 14: Monthly spend and cumulative budget
Dhaka tech team
New York team
Other operating
Contingency
Chart: 
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Dhaka tech team | 4400 | 4400 | 4400 | 4400 | 4400 | 4400
New York team | 0 | 0 | 20131 | 36462 | 59793 | 74493
Other operating | 15401 | 3350 | 11221 | 15319 | 26127 | 35098
Contingency | 1980 | 775 | 3575 | 5618 | 9032 | 11399
Month 1
$21.8K
Cumulative $21.8K
Month 2
$8.5K
Cumulative $30.3K
Month 3
$39.3K
Cumulative $69.6K
Month 4
$61.8K
Cumulative $131.4K
Month 5
$99.4K
Cumulative $230.8K
Month 6
$125.4K
Cumulative $356.2K

## Slide 15: Where the money goes
7.4%
53.6%
29.9%
9.1%
Dhaka tech salaries
$26,400
5 people × 6 months
New York team
$190,879
84 person-months: 21 staff, 63 part-time data
Other operating
$106,516
Payroll taxes, devices, legal, office, transit, cloud, marketing
Contingency
$32,379
10% of all costs

## Slide 16: Scenarios and sensitivity
Hybrid lean base: this plan
Dhaka tech + New York business, ops and data team
$356K
Premium talent
+40% Dhaka salaries and +25% New York pay
$426K
Full-time data team
21 data associates at 40 hours a week from day one
$516K
All-US engineering
5 New York engineers at about $150K a year each
$794K

## Slide 17
FUNDING REQUIREMENT
$739K
completes the six-month build and funds Months 7–9 at the launch run-rate, with no revenue assumed.
Month 6
$356.2K
Build complete, 36 people, beta live
Month 9
$739K
Three months of runway
Month 12
$1.12M
Six months of runway

## Slide 18: PathaSathi business model
Plan | Price per month | What the merchant gets
Free | $0 | Map listing, basic catalogue, 1 user, with ads
Basic | $19 | Full catalogue and orders, verified badge, customer SMS reminders, reports, no ads
Pro | $49 | Multi-staff, online storefront and delivery, marketing hub, AI advice, priority listing, no ads
Payment commission
0.5% on online payments via Stripe Connect split payments, on top of Stripe's own fee
SMS credits
Bulk SMS resold with a small margin, about US$1.50 per paid merchant per month
Ads
Banner ads for customers and free-plan merchants only, never at checkout: about US$0.08 per active customer a month

## Slide 19: How merchants get onboarded
1
Day 0
Visit and demo
A 10-minute demo on the merchant's phone, in the shop
Sales Executive
2
Same day
Free sign-up
Merchant signs up with a phone number and a map pin on the Free plan
Sales Executive
3
Days 1–3
Shop set-up
Products added by barcode or AI photo scan, plus prices, delivery zones and Stripe payouts
Sales Executive
4
First 30 days
Training and check-ins
Training in Bangla or English, check-ins in weeks 1 and 3; each merchant invites first 10 customers
Support Agent
5
Month 1–2
Upgrade to paid
When the merchant needs a verified badge, SMS reminders or an online store
$19 or $49
Year 1 funnel
3,795
merchants join and upgrade to paid
2,799
merchants still paying at year end
27,990
active customers (10 per merchant)

## Slide 20: After launch
Months 5–6
Beta
150–200 beta merchants in Queens
1,500–2,000 customers, 10 per merchant
Jackson Heights, Jamaica, Ozone Park
Fix bugs from feedback
200 ready to pay
2,000 customers
Year 1
New York City
Door-to-door merchant sales
Brooklyn and Bronx (Parkchester)
Bangla media, Facebook, TikTok
Referral: 1 free month
2,799 paid merchants
27,990 customers
Year 2
NJ and Michigan
Paterson, New Jersey
Detroit and Hamtramck
Mosque and community partners
WhatsApp broadcasts
6,789 paid merchants
67,890 customers
Years 3–5
Nationwide
Atlanta, Texas, California
Other South Asian communities
Brand-sponsored ads
Annual plans
20,290 paid merchants
202,900 customers

## Slide 21: Merchant and customer growth
1 : 10
every active merchant serves about ten active customers
Beta 150–200 merchants →
1,500–2,000 customers
Year 5 20,290 merchants →
202,900 customers
Chart: Active customers
| Beta | Month 12 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Active customers | 2000 | 12530 | 27990 | 67890 | 115870 | 162550 | 202900
 | Beta | Month 12 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Merchants | 150–200 | 1,253 | 2,799 | 6,789 | 11,587 | 16,255 | 20,290
Customers | 1,500–2,000 | 12,530 | 27,990 | 67,890 | 115,870 | 162,550 | 202,900

## Slide 22: First 6 months of revenue
Month | New merchants | Paid merchants | Customers | Subscriptions | Pay + SMS | Ads | Revenue | Cost | Net (US$)
Month 7 | 200 | 200 | 2,000 | 5,900 | 1,500 | 160 | 7,560 | 127,520 | −119,960
Month 8 | 216 | 402 | 4,020 | 11,859 | 3,015 | 322 | 15,195 | 128,159 | −112,964
Month 9 | 233 | 607 | 6,070 | 17,910 | 4,553 | 486 | 22,949 | 128,842 | −105,893
Month 10 | 252 | 817 | 8,170 | 24,088 | 6,124 | 653 | 30,865 | 129,573 | −98,708
Month 11 | 272 | 1,031 | 10,310 | 30,428 | 7,736 | 825 | 38,989 | 130,357 | −91,368
Month 12 | 294 | 1,253 | 12,530 | 36,966 | 9,398 | 1,002 | 47,366 | 131,197 | −83,831
Total | 1,467 |  |  | 127,151 | 32,326 | 3,448 | 162,924 | 775,648 | −612,724

## Slide 23: Five years revenue
Year | New paid merchants | Paid merchants at year end | Customers at year end | Ads (US$) | Revenue (US$) | Avg/month (US$)
Year 1 | 3,795 | 2,799 | 27,990 | 13,621 | 643,582 | 53,632
Year 2 | 7,287 | 6,789 | 67,890 | 49,816 | 2,353,788 | 196,149
Year 3 | 10,214 | 11,587 | 115,870 | 92,404 | 4,366,112 | 363,843
Year 4 | 12,129 | 16,255 | 162,550 | 137,530 | 6,498,273 | 541,523
Year 5 | 12,804 | 20,290 | 202,900 | 178,594 | 8,438,573 | 703,214
Total | 46,229 |  |  | 471,965 | 22,300,328 | 

## Slide 24: Break-even point
US$127,520
cost in launch month: team of 36 plus operating costs, rising as merchants grow
US$37.80
average monthly revenue per paid merchant, incl. US$0.80 from ads
~8,271
paid merchants (~82,710 customers) when revenue first covers costs, Month 27 after launch
Case | Monthly break-even | 5-year revenue
Growth case (this forecast) | Month 27 | US$22.3M
Conservative (half the merchant growth) | Month 44 | US$11.2M

## Slide 25: Profit or loss
+US$3.57M
cumulative profit after 5½ years, growth case
Month 27
after launch: first month revenue covers costs
−US$2.05M
lowest cumulative point, Month 26 after launch: the funding needed
Period | Revenue | Costs | Profit / loss | Cumulative | If growth is half
Build | 0 | 356,174 | −356,174 | −356,174 | −356,174
Year 1 | 643,582 | 1,634,208 | −990,626 | −1,346,800 | −1,551,410
Year 2 | 2,353,788 | 3,016,164 | −662,376 | −2,009,176 | −2,838,486
Year 3 | 4,366,112 | 3,821,720 | 544,392 | −1,464,784 | −3,533,594
Year 4 | 6,498,273 | 4,650,830 | 1,847,443 | 382,659 | −3,628,445
Year 5 | 8,438,573 | 5,250,573 | 3,188,000 | 3,570,659 | −3,098,776
Total | 22,300,328 | 18,729,669 | 3,570,659 |  | −3,098,776

## Slide 26: Thank you